## product backlog
Category | Perspective | item | Estimated Effort | Priority | Comments/Thoughts/Ideas | State | Related to Sprint
(A) Provide useful geographic information | User/Editor/Admin | As a User I would like to display base map and layer | 1 man/day | High | Need to connect to service first | Finished
(B) choose what to display on map | User/Editor/Admin | As a User I would like to show&hide layers (TOC) | 2 man/day | High |  | Finished
|  | As a User I would like to change layer opacity |  | Low |  | Finished
|  | As a User I would like to change basemap |  | High |  | Finished
( C ) Navigate through platform | User/Editor/Admin | As a user I would like to show full extent of map | 1 man/day | High |  | Finished
|  | As a User I would like to zoom map |  |  | zoom in and out scale | Finished
|  | As a User I would like to pan map |  |  |  | Finished
|  | As a User I would like to jump to point location |  |  |  | Finished
(D) LOD | User/Editor/Admin | As a User I would like to get overview map | 1 man/day | Medium |  | Finished
|  | As a User I would like to show/know key map |  |  | legend | Finished
|  | As a User I would like to show/know map scale |  |  |  | Finished
( E ) Search | User/Editor/Admin | As a User I would like to search on map (identify) | 3 man/day | High |  | upcoming
|  | As a User I would like to show search result on grid |  |  |  | Finished
|  | As a User I would like to search on buffer |  |  |  | upcoming
|  | As a User I would like to search on layer area by draw point/line/polygon |  |  |  | upcoming
( F ) advanced search viewing | User/Editor/Admin | As a User I would like to zoom map to the result | 2 man/day | medium |  | Finished
|  | As a User I would like to move in map according to search result |  |  |  | Finished
|  | As a User I would like to highlight search results/features |  |  |  | Finished
(G) Printing | User/Editor/Admin | As a User I would like to print map | 1.5 man/day | High |  | Finished
| Editor/ Admin | As a Editor/ Admin I would like to print map on template | 1.5 man/day | High |  | upcoming
(H) Measuring | User/Editor/Admin | As a User I would like to measure distance by line or polygon | 1 man/day | medium |  | Finished

## sprint backlog
User Story | Perspective | Task | Related story | Estimated Cost | Status | Comments | Responsible | #of task on TFS
|  |  |  | low/medium/high | in progress/done/upcoming
### Sprint(1) ###
As a developer I need to design a system blueprint | Developer | Discuss and decide the system structure |  |  | done
|  | Discuss and decide the class diagram |  |  | done |  | Refaat
|  | Discuss and decide about database system. |  |  | done
|  | Make a first draft of an user interface |  |  | done |  | Swaify
|  | Discuss and decide about database connection secure |  |  |  |  | refaat
start system archticture implementation | Developer | Implement database schema |  |  | done |  | Refaat
implment backend/frontend connection (DB) & service connection ( basic map view)
connect func with UI design
As a developer I need to publish/view/navigate map service | Developer | publish map services | A&B&C |  | done |  | Ramdan
|  | develop TOC |  |  | done |  | Ramdan
|  | Develop change basemap function |  |  |  | No basemap provided till now
|  | Develop change opacity function |  |  | done
|  | develop full extent map function |  |  | done |  | Ramdan
|  | develop zoom in and out function |  |  | done |  | Ramdan
|  | previous extent |  |  | done |  | Ramdan
|  | next extent |  |  | done |  | Ramdan
|  | develop pan function |  |  | done |  | Ramdan
|  | develop overview map |  |  | done |  | Ramdan
|  | develop scale function |  |  | done |  | Ramdan
|  | develop key map |  |  | done |  | Ramdan
### Sprint (2) ###
As a developer I need to develop search functions | Developer | develop default search function | E&F |  | done |  | rafa + Ramdan
|  | develop customized search function to search on layers |  |  |  |  | rafa + Ramdan
|  | develop customized search function to search with buffer |  |  |  |  | rafa + Ramdan
|  | develop customized search function to show result on grid |  |  | done |  | rafa + Ramdan
|  | develop function to move in map according to search result |  |  | done |  | rafa + Ramdan
|  | develop search function to go to point by x,y |  |  |  |  | rafa + Ramdan
As a developer I need to create draw tools | Developer | develop tools option like point, line and polygon | E&H |  |  |  | Ramdan
|  | develop measure funtion by drawing tools |  |  | done |  | Ramdan
|  | develop search function by drawing tools |  |  |  |  | Ramdan
As a developer I need to create print module | Developer | establish database connection | G |  | done |  | ref3at
|  | create Role table in database |  |  | done |  | ref3at
|  | develop login function |  |  | done |  | refa3t
|  | develop print function to print web map |  |  |  |  | ramdan | 2016-03-23
|  | develop print function to print map on templete |  |  |  |  | ramdan | 2016-03-23
As a developer I need to create advanced search function and interact with the design | Developer | search function & highlight result |  |  |  |  | ref3at
|  | identify |  |  | done |  | ramdan
### Sprint (3) ###
As a developer I need to finish development | developer | Test system
create documentation